## Sheet1
Project Name | Online shopping portal for mycompany.com
Project Code | PRJ-2014/101
Element code | Module | Description | Module Name | Responsible Person | Team Members
01.01.01 | 01. Login module | Registration page for buyers | 01. Login module | Talakisew | James Singh
01.01.02 | 01. Login module | Common login page for admin, vendors, buyers and internal users. | 02. Customer Module | Yogendra Pant | Va Yim
01.01.03 | 01. Login module | Separate login page for buyers for when they choose to login prior to checkout. | 03. Vendor Module | Yogendra Pant | Yogendra Pant
02.01.01 | 02. Customer Module | Homepage with customers containing links to all the pages he can visit. | 04. Admin Module | Weldu | Talakisew
02.01.02 | 02. Customer Module | Update billing and or shipping address | 05. Listener Codes | Weldu | Weldu
02.01.03 | 02. Customer Module | Add/Edit/Delete payment details (for visa and master card) | 06. Reports Module | Md Mojahidul Islam | Md Mojahidul Islam
03.01.01 | 03. Vendor Module | Vendor homepage containing links to all the pages s/he can visit. | 07. Finance and Payment Gateway | Md Mojahidul Islam
03.01.02 | 03. Vendor Module | manage vendor profile | 08. Product Browsing Module | Va Yim
03.01.03 | 03. Vendor Module | Add/Delete/Update/List/View products | 09. Shopping cart Module | Va Yim
04.01.01 | 04. Admin Module | List ACL (and edit?) from Active directory | 10. Invoice Module | Talakisew
04.01.02 | 04. Admin Module | Add/Delete/Update/List/View internal users, with their ACL | 11. Payment Module | Talakisew
04.01.03 | 04. Admin Module | Add/Delete/Update/List/View customers, with their ACL | 12. Receipt generation Module | James Singh
04.01.04 | 04. Admin Module | Enable/Disable customer, vendor and buyer accounts | 13. SMTP the delivery details automatically | James Singh
04.01.05 | 04. Admin Module | Display and update commission on settings page. | 14. User Friendly Interface | James Singh
04.01.06 | 04. Admin Module | Add/Update/disable/enable categories
05.01.01 | 05. Listener Codes | Listener code that will create around 10 credit card details when the application starts up (if not exist already)
05.01.02 | 05. Listener Codes | Listener code that will create 1 admin user to database on application startup (if not exist already)
05.01.03 | 05. Listener Codes | Listener code that will create a commission record to the database on application startup (if not exist already)
06.01.01 | 06. Reports Module | Generate sales report for mycompany.com with filters for date range, vendor range, and sort by quantity and price of product price and transaction total amount.
06.01.02 | 06. Reports Module | Generate report listing all vendors with filter by name, and address attributes
06.01.03 | 06. Reports Module | Generate report listing all buyers with filter by name and address attributes
06.01.04 | 06. Reports Module | Generate report listing all internal users by their department.
07.01.01 | 07. Finance and Payment Gateway | Develop a RESTful webservice ready application for myfinance.com application
07.01.02 | 07. Finance and Payment Gateway | Develop a RESTful webservice ready application for payment world
07.01.03 | 07. Finance and Payment Gateway | The payment gateway application should be able to process payment request
07.01.04 | 07. Finance and Payment Gateway | The myfinance application should be able to save finance details upon such call from mycompany.com website.
08.01.01 | 08. Product Browsing Module | Display list of products to customer
08.01.02 | 08. Product Browsing Module | Display product categories on the side of product list
08.01.03 | 08. Product Browsing Module | Display products belonging to given category when the category is clicked.
08.01.04 | 08. Product Browsing Module | Display products by a given vendor when vendor name is clicked
08.01.05 | 08. Product Browsing Module | Display product detail page when the user clicks on listed product
08.01.06 | 08. Product Browsing Module | Display 'Add to cart' button along with textfield with product count defaulted to '1'
09.01.01 | 09. Shopping cart Module | Add to shopping cart backend code, and integration with UI from 101.08.WBS006
09.01.02 | 09. Shopping cart Module | Display Shopping cart with added products, and Checkout button
09.01.03 | 09. Shopping cart Module | Remove products from shopping cart and update product quantity (should be within limits)
09.01.04 | 09. Shopping cart Module | On proceeding from cart, if the user is not logged in, allow him to login as a registered user, or proceed as a guest user.
09.01.05 | 09. Shopping cart Module | Confirm billing and delivery address for the buyer.
09.01.06 | 09. Shopping cart Module | Display purchase details to the user, and allow him to make payment by clicking on 'Make Payment' button.
09.01.07 | 09. Shopping cart Module | Display message on successful purchase.
10.01.01 | 10. Invoice Module | Generate invoice and save it on successful purchase.
11.01.01 | 11. Payment Module | Integrate with payment gateway for payment processing.
11.01.02 | 11. Payment Module | Integrate with myfinance.com to save transaction details on successful payment processing.
12.01.01 | 12. Receipt generation Module | Generate receipt and save it on successful payment processing.
13.01.01 | 13. SMTP the delivery details automatically | On successful purchase, email the buyer along with receipt and invoice details.
14.01.01 | 14. User Friendly Interface | 01. Login module
14.01.02 | 14. User Friendly Interface | 02. Customer Module
14.01.03 | 14. User Friendly Interface | 03. Vendor Module
14.01.04 | 14. User Friendly Interface | 04. Admin Module
14.01.05 | 14. User Friendly Interface | 05. Listener Codes
14.01.06 | 14. User Friendly Interface | 06. Reports Module
14.01.07 | 14. User Friendly Interface | 07. Finance and Payment Gateway
14.01.08 | 14. User Friendly Interface | 08. Product Browsing Module
14.01.09 | 14. User Friendly Interface | 09. Shopping cart Module
14.01.10 | 14. User Friendly Interface | 10. Invoice Module
14.01.11 | 14. User Friendly Interface | 11. Payment Module
14.01.12 | 14. User Friendly Interface | 12. Receipt generation Module
14.01.13 | 14. User Friendly Interface | 13. SMTP the delivery details automatically
Note on C37: Will start to implement next week -Va Y.
Note on C34: Will start this week after the 08.01.03 -Va Y.
Note on C31: Start after Project structure has been setup -Va Y.